## Current Month
Dashboard
The Process:
The process is going nice with the kanban model.
We just pick away at the kanban board one by one,
keeping merges simple and easy.
Tasks realized during this cycle:
-Relational database setup | -class.php, gets session variables to keep quizzes and polls related, displays all students in a class and all quizzes made for that class.
-DDL file | -Save_poll.php, takes the form from createQuiz and inserts it in the database
-Header.php to be included in all pages | -Signup.php, uses server-side validation to create a new student or instructor and inserts in the database.
-dbConnection.php to start the php connection to localhost | -Users can login as student or teacher
-Index.php, homepage for signup and login | -Login.php, uses server side validation to check if a user is in the system.
-createQuiz.php, adding polls to the quiz through a public form. | -Styling for all of these pages was added to enhance the user experience.
-classes.php to search for classes by school and display all classes for that school.
Summary of the progress:
-During this cycle we accomplished a number of tasks from our task board | -Implemented a file to include in all php files that need to establish a connection to the database
-We implemented a full sql database file to set up our database based on our design. | -Implemented the create quiz functionality that uses server side validation to check if a quiz name already exists for that class,
-We implemented a signup page where users can sign up as either a teacher or a student. | uses session variables to track which class the quiz is for and which quiz added questions are for.
The page uses server side validation to make sure the email and username entered is not already in our system. | -Added a class page that displays all students and quizzes for a specific course. This page is where you create a new quiz from.
If not, the user’s data will be added into our database student or teacher tables. | -Added a page to where you can search for class by school name and selecting the class will take you to the class page as described above.
Their passwords were encrypted using md5 encryption to add a layer of security for the user. | Selecting a class will store the class name and school as session variables to be used to display the class.php file and for DML when creating a quiz to keep everything related.
-A login page was also implemented which validates the user is in our system before logging them in.
-A header was implemented which contains the site logo and navigation buttons for the site.
This header will display on all pages.

## Sheet1
timeline (days) | Ideal Tasks Remaining | Actual Taskes Remaning
1 | 14 | 14
2 | 12 | 12
3 | 10 | 11
4 | 8 | 8
5 | 6 | 5
6 | 4 | 3
7 | 2 | 2
8 | 1 | 1

## CHART DATA (hidden)
CHART DATA
| Projected | Actual
Cash Flow | #REF! | #REF!
Monthly Income | #REF! | #REF!
Monthly Expense | #REF! | #REF!