## Dashboard
DASHBOARD
KANBAN TASK CARD | PERSON | TO DO | DOING | DONE | TO DO | DOING | DONE | TO DO | DOING | DONE
TASKS REMAINING |  |  |  |  | TASKS REMAINING
Student portal
Dashborad
The Process is still going nicley, the Kanban Model makes it easy to see what is done, what is being worked on and what still needs to be done, making group collaberation easy.
Edit/Delete quizzes from a class.
Teacher create a class
List a class for teachers
Student portal
Dashborad
Edit/Delete quizzes from a class.
List a class for teachers
Student portal
Teacher create a class
Dashborad
WG
MV
AV
EJ
Edit/Delete quizzes from a class.
List a class for teachers
Student portal
Teacher create a class
Dashborad
WG
MV
MV
AV
EJ
Student portal
Teacher create a class
Dashborad
MV
AV
EJ
Edit/Delete quizzes from a class.
WG
List a class for teachers
MV
START OF WEEK
MID WEEK
END OF WEEK
Start Quiz
Push started quiz to class
Style some pages
Add User security to the pages

## DATA
timeline (days) | Ideal Tasks Remaining | Actual Taskes Remaning
1 | 5 | 5
2 | 4.375 | 4
3 | 3.75 | 4
4 | 3.125 | 3
5 | 2.5 | 2
6 | 1.875 | 1
7 | 1.25 | 1
8 | 0.625 | 0